# Quantara POS — Master Plan

## 1. Goal

- Launch Quantara, a multi-tenant POS SaaS for restaurants & cafés, live at Electro Café on Tue 10 Nov 2026.

- Build it as a product, not a client project: Electro Café is tenant #1; everything client-specific is a setting.

## 2. Success on 10 Nov

- Cashiers at Electro Café sell, take payment (SYP / USD, cash, card, wallets), print prep tickets and close shifts — with or without internet.

- HQ manages menu, prices, exchange rate and sees daily sales per branch.

- A new cashier is productive after 30 minutes of training (GEN-05).

- Zero lost orders during power/internet cuts (OFF-01, OFF-08).

- A second tenant could be onboarded without code changes (GEN-01, GEN-02).

## 3. Scope

- Master list: requirements — 111 requirements (87 Must, 105 Launch).

- Excluded: out-of-scope — tables, QR ordering, reservations, loyalty, mall-% module, deferred sales.

- 10-Nov cut: 105 “Launch” items do not fit 6 weeks. A proposal is in the Nov-10 column (66 IN · 14 MIN · 23 LATER · 8 TBD) — see scope-nov10. Confirmed in the scope-cut session (Wed 30 Sep), driven by D-21.

- Three surfaces, in priority order:

  - Cashier app (+ customer display, prep tickets) — must be complete.

  - Tenant back office — essentials only (catalogue, prices, exchange rate, users, shift & sales reports).

  - Operator control panel — minimum to onboard and support one tenant; rest after launch.

## 4. Timeline

Work week assumed Sun–Thu (confirm). Design runs one sprint ahead of development.

Sprints are 1 week, Sun–Thu, named as in Jira. The backend builds one module at a time, starting a module only when it passes the readiness gate (HTML complete, flows, handoff doc, decisions, stack). Figma gates the front end, not the backend.

| Phase | Dates | Backend module | Design · PO / HTML | Gate |
| --- | --- | --- | --- | --- |
| Sprint 1 — Design first | Sun 20 Sep – Fri 2 Oct | — | Research, HTML prototype (all 111 requirements), panel in Figma | — |
| Planning gate | Mon 28 Sep – Thu 1 Oct | — | Scope cut, decisions group A, ADR-001 stack, Module 1 handoff | G1: Ready to build (Thu 1 Oct) |
| Sprint 2 — Platform core | Sun 4 – Thu 8 Oct | M1 tenants, branches, registers, users & roles, catalogue (plan) | Figma: platform core + cashier sale & payment · HTML: offline & power cut · M2 handoff | Decisions group B closed |
| Sprint 3 | Sun 11 – Thu 15 Oct | M2 Sale → payment → invoice → prep ticket, online + offline | Figma: shift close, invoices, kitchen · HTML: mixed payment, shift close | — |
| Sprint 4 | Sun 18 – Thu 22 Oct | M3 Shift & cash drawer, cancel/refund, printing, sync conflicts · hardware ordered | Figma: back office essentials | Decisions group C closed |
| Sprint 5 | Sun 25 – Thu 29 Oct | M4 Back office: prices & offers, exchange rate, reports, inventory (per D-01) · M5 Quantara minimum | States, polish · UAT script | G2: Feature complete (Thu 29 Oct) |
| Hardening & UAT | Sun 1 – Thu 5 Nov | Bug fixing, performance | Client UAT sign-off, menu data loaded | G3: UAT signed (Thu 5 Nov) |
| Install & training | Sat 7 – Mon 9 Nov | Hardware on site, dry run | Staff trained | G4: Go / no-go (Mon 9 Nov) |
| Go-live | Tue 10 Nov | Live at Electro Café, hyper-care 2 weeks |  | — |

## 5. Team & roles

| Role | Who | Owns |
| --- | --- | --- |
| Product Owner | Sankari DT (PO) | Scope, priorities, decisions, this plan |
| Designer | Mariam Kabbani | Figma, screen registry |
| Developers | 1 backend developer (name TBD — by 1 Oct); front end TBD | Build, ADRs, module handoffs |
| QA | TBD | Test cases, UAT support |
| Client owner | Electro Café owner | Business decisions |
| Client technical contact | TBD (D-20) | Site, hardware, UAT |
| PO agent (Claude) | Scheduled daily | Daily report, drift & risk flags |

## 6. How we work

- Truth lives in the repo; Jira tracks work; Figma holds visuals; Drive holds human/client docs. See CLAUDE.md.

- Cadence: daily report (PO agent, 09:00) · daily 15-min stand-up · weekly sprint review & planning (Thu) · weekly client check-in (decisions).

- Gates: Definition of Ready / Done in po-playbook; module readiness in module-readiness.

- Jira: everything in POSD — design, PO and backend (label backend, one epic per module).

- Change control: after G1, any scope addition needs a decision-log entry and must name what moves out.

## 7. Top risks

Full list: risk register. 1. Scope too large for 6 weeks → scope cut on 30 Sep, weekly re-check. 2. Open decisions block build → owners & dates in decision log. 3. Offline sync bugs (duplicates, conflicts, double printing) → offline behaviour settled in HTML before M2 (Sprint 3); tested with real cuts. 4. Local payment integrations (Syriatel Cash, Sham Cash, cards) → spike at the start of M2 (Sprint 3); manual-record fallback. 5. One backend developer → one module per sprint, strict P0/P1/P2; stack must be accepted by Thu 1 Oct or the backend can’t start 4 Oct. 6. IP ownership not in writing (D-22) → sign before G1.

## 8. Key links

- Requirements · Decision log · Screen registry · Delivery plan · Risk register · PO playbook (all in docs/)

- Jira POSD: https://sankari-holding.atlassian.net/browse/POSD

- Figma: TBD · Drive folder: TBD

## 9. Change history

| Version | Date | Change |
| --- | --- | --- |
| 1.0 | 28 Sep 2026 | First version |
| 1.1 | 28 Sep 2026 | Sprints renamed as in Jira (design sprint = Sprint 1); backend builds one module per sprint behind a readiness gate; team: designer named, 1 backend developer |